Study update – TUV

Study: H-29

Date: 30th October 2022

| Study: | H-29 Delta Multihole TT |
| --- | --- |
| Number of sites: | 1 |
| Recruitment period: | June 2022 – ongoing |
| No. of patients included: | 3 |
| Number of patients at 2 yr. FU: | 3 |
| Serious Adverse Events Device Related | 0 |
| Study status | Enrollment |
| Notes: | Retrospective study. Study activation: 22Feb2022 Total sample size expected: 50 First patient enrolled: 06Jun2022 The time frame between study activation to first patient enrolled is due to lack of personnel. A SubI was recently included in the study team to work on data entry of patient data in Limes (data are already available since this is a retrospective study). We expect a faster data entry in the coming weeks. |

Study update – TUV

Study: H-34

Date: 30th October 2022

| Study: | H-34 Delta Revision |
| --- | --- |
| Number of sites: | 1 |
| Recruitment period: | September 2021 – ongoing |
| No. of patients included: | 13 |
| Number of patients at 2 yr. FU: | N/A |
| Serious Adverse Events Device Related | 2 |
| Study status | Enrollment |
| Notes: | Prospective study Study activation: 27Jul2021 Total sample size expected: 49 First patient enrolled: 14Sep2021 The study is still in the enrollment phase, only 6 patients completed 6 months FU |

Da inviare a Rossella Grosso con Federica e Magalì in cc