| Study ID and title: | H-34 DELTA Revision |
| --- | --- |
| Date: | 04/02/2025 |
| Site: | 101 - Samodzielny Publiczny Szpital Kliniczny im. Prof. Adama Grucy CMKP |
| Principal Investigator: | Dr. Jerzy Bialcki |

From: Aissa Benyattou NAMSA CSM

To: LimaH34 TMF

Subject:  H-34 DELTA REVISION Delay for finalizing the monitoring report for site 101

Issue:

The reports for the following visits listed in the table below signed with delay. The timelines for the finalization of visit report are 10 business days, as per Monitoring Plan V1.1 15/Sept/2021. Timeline for report finalization was not respected for the following monitoring visits:

|  | Visit #: 1 | Visit #: 2 | Visit #: 3 | Visit #: 4 | Visit #: 5 | Visit #: 7 |
| --- | --- | --- | --- | --- | --- | --- |
| MV date | 18/11/2021 | 03/02/2022 | 09/06/2022 | 04/11/2022 | 17/05/2023 | 26/09/2024 |
| Report Signed on | 07/12/2021 | 18/02/2022 | 28/06/2022 | 21/11/2022 | 28/06/2023 | 21/10/2024 |
| Report should be signed per M plan | 02/12/2021 | 17/02/2022 | 23/06/2022 | 18/11/2022 | 31/05/2023 | 10/10/2024 |
| Delay per day | 3 | 1 | 3 | 1 | 20 | 7 |

Resolution:

Ensure compliance with the monitoring plan for future visits.

Author

Aissa Benyattou NAMSA CSM

Name/Title                                                                                   Signature                                                              Date

Approver

Name/Title                                                                                   Signature                                                              Date

For filling in Trial Master File