## Queries_pending
Pt ID | FOLLOW UP | QUERY | ACTION | Sponsor comment | STATUS | SITE COMMENT
101/1 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/1 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING |  | Status
101/1 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING |  | PENDING
101/1 | FU 6 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING |  | SOLVED
101/1 | FU 1 year | No data inserted in the eCRF | Please complete the "FU 1 year" section of the eCRF |  | PENDING
.
101/2 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/2 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload
101/2 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
.
101/4 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/4 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/4 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/4 | FU 6 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
.
101/5 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/5 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/5 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/5 | FU 6 months | No data inserted in the eCRF | Please complete the FU 6 months section of the eCRF |  | PENDING
.
101/6 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/6 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
|  | . |  |  | PENDING
101/7 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/7 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/7 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/7 | FU 6 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/7 | FU 6 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/7 | FU 1 year/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
.
101/8 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/8 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/8 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/8 | FU 6 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/8 | FU 1 year/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/8 | FU 1 year/HHS | In the section "Absence of deformity" no option was selected, however it seems to not fit with the other data reported (other values are all good) | Please review this field |  | PENDING
.
101/9 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
.
101/10 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/10 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/10 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/10 | FU 6 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/10 | FU 1 year/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/10 | FU 1 year/HHS | In the section "Absence of deformity" no option was selected, however it seems to not fit with the other data reported (other values are all good) | Please review this field |  | PENDING
.
101/11 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/11 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/11 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/11 | FU 6 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
.
101/13 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/13 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/13 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/13 | FU 6 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
.
101/14 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/14 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/14 | Reoperation 1/adverse event and implant surgery | The section and "implant surgery" was not validated | Please validate this section |  | PENDING
.
101/15 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/15 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/15 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
.
101/16 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/16 | Patient data | From the section "batch number"expiry date" it can be deduced that the stem was not implanted and it is from a competitor | Please insert the following statement in the "Notes" of "patient data" section: "Delta Revision Cup has been implanted in coupling with a competitor stem, because the stem was well osteointegrated. There was no need to remove it." |  | PENDING
101/16 | Intraoperative/Surgery data | In the section "Acetabulum", "bone grafting" indicated as "NO", however "graft material" section was reported as "Missing data" | If a bone grafting has not been done, please correct the "graft material" section with "-" |  | PENDING
101/16 | Intraoperative/Surgery data | In the section "Femur", "bone grafting" indicated as "NO", however "graft material" section was reported as "Other" | If a bone grafting was not performed, please correct the "graft material" section with "-". In case a bone grafting was performed, please correct the section with "YES" and complete the subsection with the graft material used. |  | PENDING
101/16 | Intraoperative/Batch number/expiry date | In the section "femoral stem" date of primary surgery missing | If available, please add the date of the primary surgery in which the femoral stem was implanted |  | PENDING
101/16 | Intraoperative/Batch number/expiry date | In the section "femoral head" date of surgery missing | Please add the date of the surgery in which the femoral head was implanted |  | PENDING
101/16 | Intraoperative/Batch number/expiry date | Centralizer: to the question "has a new centralizer been implanted?" the answer is "-" | Please correct "-" with "no" if no new centralier was implanted |  | PENDING
101/16 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/16 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/16 | FU 2 months/HHS | To the question "activities/public transportation" no answer was given | Please review this field |  | PENDING
.
101/17 | All sections | No data inserted in the eCRF | Please review this patient and complete the sections with missing data.
.
101/18 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/18 | Patient data | From the section "batch number"expiry date" it can be deduced that the stem was not implanted and it is from a competitor | Please insert the following statement in the "Notes" section of "patient data": "Delta Revision Cup has been implanted in coupling with a competitor stem, because the stem was well osteointegrated. There was no need to remove it." |  | PENDING
101/18 | FU at discharge | The field has not been completed | Please revise this field and complete it as soon as new information become available |  | PENDING
.
101/19 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/19 | Intraoperative | In the sections "stem" and "cup", the field "cement" was reported as "no" | Please select "N/A" in both fields
101/19 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/19 | FU at discharge/Radiographical evaluation | "X-rays date" of FU at discharge is the same as "Preoperative" | Please double check this field and correct it accordingly |  | PENDING
101/19 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
.
101/20 | Preoperative | The section "preoperative" was not validated | Please, to validate |  | PENDING
101/20 | Preoperative/preoperative data | The section "relevant medical history including any significant disease" contains the description of a THA on the affected side | Please review this field and move any relevant information related to the affected hip side to the section "previous hip treatments or surgeries on the affected side/if yes, please specify" |  | PENDING
101/20 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/20 | Patient data | From the section "batch number"expiry date" it can be deduced that the stem was not implanted and it is from a competitor | Please insert the following statement in the "Notes" of "patient data" section: "Delta Revision Cup has been implanted in coupling with a competitor stem, because the stem was well osteointegrated. There was no need to remove it." |  | PENDING
101/20 | Intraoperative/batch number and expiry date | The section "femoral stem/if not, please specify the manufacturer and date of the primary surgery" was not completed | Please complete this field with the missing information |  | PENDING
101/20 | Intraoperative/batch number and expiry date | The section "femoral head/if yes and if manufactured by Lima, please specify the femoral head batch number" was not completed | Please complete this field with femoral head batch number |  | PENDING
101/20 | FU at discharge/Radiographical evaluation | The field has not been completed | Please revise this field and complete it as soon as new information become available |  | PENDING

## Missing x-rays
Pt ID | FOLLOW UP | QUERY | ACTION | Sponsor comment | STATUS | SITE COMMENT
101/1 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/1 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/1 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/1 | FU 6 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/1 | FU 1 year | No data inserted in the eCRF | Please complete the FU 6 months section of the eCRF |  | PENDING
.
101/2 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/2 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload
101/2 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
.
101/4 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/4 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/4 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/4 | FU 6 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
.
101/5 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/5 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/5 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/5 | FU 6 months | No data inserted in the eCRF | Please complete the FU 6 months section of the eCRF |  | PENDING
.
101/6 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/6 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
.
101/7 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/7 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/7 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/7 | FU 6 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/7 | FU 6 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/7 | FU 1 year/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
.
101/8 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/8 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/8 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/8 | FU 6 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/8 | FU 1 year/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/8 | FU 1 year/HHS | In the section "Absence of deformity" no option was selected, however it seems to not fit with the other data reported (values all very good) | Please double check this field |  | PENDING
.
101/9 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/9 | Reoperation 1/adverse event | The section "adverse event" was not validated | Please, to validate |  | PENDING
.
101/10 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/10 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/10 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/10 | FU 6 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/10 | FU 1 year/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/10 | FU 1 year/HHS | In the section "Absence of deformity" no option was selected, however it seems to not fit with the other data reported (values all very good) | Please double check this field |  | PENDING
.
101/11 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/11 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/11 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/11 | FU 6 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
.
101/13 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/13 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/13 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/13 | FU 6 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
.
101/14 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/14 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/14 | Reoperation 1/adverse event and implant surgery | The sections "adverse event" and "implant surgery" were not validated | Please, to validate |  | PENDING
.
101/15 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/15 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/15 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/15 | FU 6 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
.
101/16 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/16 | Patient data | Stem is from competitor and has not been removed | Please insert the following statement in the "Notes" of "patient data" section: "Delta Revision Cup has been implanted in coupling with a competitor stem, because the stem was well osteointegrated. There was no need to remove it." |  | PENDING
101/16 | Intraoperative/Surgery data | In the section "Acetabulum", "bone grafting" indicated as "NO", however "graft material" section was reported as "Missing data" | If a bone grafting has not been done, please correct the "graft material" section with "-" |  | PENDING
101/16 | Intraoperative/Surgery data | In the section "Femur", "bone grafting" indicated as "NO", however "graft material" section was reported as "Other" | If a bone grafting was not performed, please correct the "graft material" section with "-". In case a bone grafting was performed, please correct the section with "YES" and complete the subsection with the graft material used. |  | PENDING
101/16 | Intraoperative/Batch number/expiry date | In the section "femoral stem" date of primary surgery missing | If available, please add the date of the primary surgery in which the femoral stem was implanted |  | PENDING
101/16 | Intraoperative/Batch number/expiry date | In the section "Femoral head" it is reported that ha new femoal head was implanted from Zimmer. However, in the field "Intraoperative/head" it was stated that the head used is "modular, Biolox® Delta" | Please revise this field, correct it accordingly and include details about batch number and expiry date | DA RIVEDERE | PENDING
101/16 | Intraoperative/Batch number/expiry date | Centralizer: to the question "has a new centralizer been implanted?" the answer is "-" | Please correct "-" with "no" if no new centralier was implanted |  | PENDING
101/16 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/16 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/16 | FU 2 months/HHS | To the question "activities/public transportation" no answer was given | Please double check this field |  | PENDING
.
101/18 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/18 | Patient data | Stem is from competitor and has not been removed | Please insert the following statement in the Notes section of patient data: "Delta Revision Cup has been implanted in coupling with a competitor stem, because the stem was well osteointegrated. There was no need to remove it." |  | PENDING
101/18 | Intraoperative/Batch number/expiry date | In the section "Femoral head" it is reported that ha new femoal head was implanted from Zimmer. However, in the field "Intraoperative/head" it was stated that the head used is "modular, Biolox® Delta" | Please revise this field, correct it accordingly and include details about batch number and expiry date | DA RIVEDERE | PENDING
101/18 | FU at discharge | The field has not been completed | Please revise this field and complete it as soon as new information become available |  | PENDING
.
101/19 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/19 | Intraoperative | In the sections "stem" and "cup", the field "cement" was reported as "no" | Please select "N/A" in both fields
101/19 | FU at discharge/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/19 | FU at discharge/Radiographical evaluation | "X-rays date" of FU at discharge is the same as "Preoperative" | Please double check this field and correct it accordingly |  | PENDING
101/19 | FU 2 months/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
.
101/20 | Preoperative | The section "preoperative" was not validated | Please, to validate |  | PENDING
101/20 | Preoperative/preoperative data | The section "relevant medical history including any significant disease" describes a surgery on the side of the revision | Please revise this field and move any information related to the affected hip side to the section "previous hip treatments or surgeries on the affected side/if yes, please specify" |  | PENDING
101/20 | Preoperative/Radiographical evaluation | Missing X-rays | Please, to upload |  | PENDING
101/20 | Patient data | Stem is from competitor and has not been removed | Please insert the following statement in the "Notes" of "patient data" section: "Delta Revision Cup has been implanted in coupling with a competitor stem, because the stem was well osteointegrated. There was no need to remove it." |  | PENDING
101/20 | Intraoperative/batch number and expiry date | The section "femoral stem/if not, please specify the manufacturer and date of the primary surgery" was not completed | Please complete this field with the missing information |  | PENDING
101/20 | Intraoperative/batch number and expiry date | The section "femoral head/if yes and if manufactured by Lima, please specify the femoral head batch number" was not completed | Please complete this field with femoral head batch number |  | PENDING
101/20 | FU at discharge/Radiographical evaluation | The field has not been completed | Please revise this field and complete it as soon as new information become available |  | PENDING

## Queries_solved
Pt ID | FOLLOW UP | QUERY | ACTION | Sponsor comment | STATUS | SITE COMMENT
101/4 | FU 2 months/ Oxford | Results from OHS were not reported in the CRF | Please add the OHS results to the CRF accordingly |  | SOLVED
101/4 | FU 6 months/ Oxford | Results from OHS were not reported in the CRF | Please add the OHS results to the CRF accordingly |  | SOLVED
101/5 | Patient data | Detail about "Intensity of activity daily living" missing | Please complete if this information is available |  | SOLVED
101/5 | Adverse event 20/10/2021 | Adverse event is reported as ANTICIPATED | expectedness should be evaluated only if the SAE is related to the procedure or to the device. In this case is not related, thus in this case should be selected N/A option |  | SOLVED
101/7 | Patient data | Detail about "Intensity of activity daily living" missing | Please complete with this information if available |  | SOLVED
101/9 | Intraoperative/surgery data | Under "Acetabulum" bone graftig is indicated as "NO", however graft material is indicated as "MISSING DATA" | Please correct "MISSING DATA" with "-" |  | SOLVED
101/9 | Intraoperative/surgery data | Under "Femur" bone grafting is indicated as "missing data" | Please complete this field with "yes" or "no" if the information is available |  | SOLVED
101/9 | Adverse event 01/12/2021 | Outocome of the event mentioned as "ONGOING" , although report type is marked as "initial &final" | Please consider adjusting "outcome of the event" accordingly | Since the surgery date was december 2021, we expecte that the event is now recovered. Please to adjust it in the eCRF section. | SOLVED
101/10 | Patient data | Detail about "Intensity of activity daily living" missing | Please complete if this information is available |  | SOLVED
101/10 | Patient data | Note indicating that the cup was impanted with a competitor stem is located under "adverse event notes" | Please move the statement to the "patient data" NOTE section | In this cases we have not to consider this event as an AE/SAE so please report it in the NOTE section of Patient Data. | SOLVED
101/11 | Intraoperative/surgery data | "Antithrombotic profilaxis" indicated as "NO", however a treatment is specified | Please change "NO" with "YES" |  | SOLVED
101/11 | Intraoperative/surgery data | In the section "Acetabulum", "bone grafting" indicated as "NO" however "graft material" section has been reported as "Other" | If a bone grafting has not been done, please to correct the "graft material" section with "-", otherwise if a bone grafting had been done please to correct the section with "YES" and the subsection with the graft materiual used. |  | SOLVED
101/11 | FU 2 months/Radiographical evaluation | in the section "Osteolysis" no selection was made between "absent/present" | since the Osteolysis acetabular zone 1 has been filled with > 2mm, Please correct with "PRESENT" |  | SOLVED
101/13 | Adverse event 12/04/2022 | Report type indicated as "initial" | Since it seems that the AE has been resolved during the surgery, please to update the report as "Final" and update the "Outcome of the Event" with the date. |  | SOLVED
101/14 | Adverse event 04/06/2022 | Adverse event reported as "initial" | since the SAE started in 04 June 2022, we expecte it is recovered now so please update the following sections: - Report type - Outcome of the event - Current clinical status - “Was the device permanently removed?” - Detailed treatment |  | SOLVED
101/15 | Patient data | Stem is from competitor and has not been removed | Please insert the following statement in the Notes section of patient data: "Delta Revision Cup has been implanted in coupling with a competitor stem, because the stem was well osteointegrated. There was no need to remove it." |  | SOLVED
101/15 | FU at discharge/Radiographical evaluation | Osteolysis indicated as "ABSENT", although specified as "PRESENT" in Acetabular Zone | Please correct osteolysis as "PRESENT" |  | SOLVED